## BC History
Broderick Creek Flow-Through Dump Development
Original compilation by Bruce Hutchison May 2008
Abbreviations:
BJH Bruce Hutchison
BC Broderick Creek
BCFT Broderick Creek Flow-Through
BCD Broderick Creek Dump
BCDiv PMI Broderick Creek Diversion channel
Notes: | - Surpac files extracted from end of month surfaces using bcvalley/bcrkbdy1.str
- High tree cover hid much of creek in airphotos so exact location is not known
- an elevation change was made to sea level datum and a 3m difference was noted across part of mine site during ABM's early mining phases
- it is not known if this possibility has an effect on the orignal airphoto
- location of creek (x,y,z) in Surpac files was therefore interpreted by BJH
Date | Event | Surpac string files: bcvalley/
| Natural surface | natural sfc/nat1_creek
| Original creek | nat_creek
| Creek extrapolated to RL400 (above dtm surfaces) | nat_creek_rl400
mid1980's | PMI start operations on north side of river
PMI hillside dumps evolve
PMI dig BC diversion channel and construct diversion dam to prevent inflow into South Lens ( or to at least reduce the flow).
PMI flow-through begins construction
| PMI flow-through completed | 1996_preabm/pre-abm_96_1
| PMI overflow spillway to South Lens constructed | 1996_preabm/pre-abm_96_1
end of 1995 | PMI leave site (PMI dumps completed) | 1996_preabm/pre-abm_96_1 | Note: PMI dumps appear to have either covered original creekbed and/or pushed it to western side
Pickup of BCDiv is 3m higher than Dec03 airphoto pickup. (This may be related to the sea level datum change)
BCDiv is approximately 26m higher than original creekbed
1997-1998 | ABM start mining and begin sidehill dumping of clay from ROM along PMI dumps (conversation BJH with Dave Sandy) | 1998/bcdump_01_98 | Survey files do not show any change to creek bed but these may not have been surveyed at the time.
1999-06-01 | BCFT well developed from N8500-N9500 (see sheet June 1999) | 1999/bcdump_06_99 | still open water near N9200-N9400
1999-07-01 | July EOM reports "that flow capacity of the Brett's drainage pipeworks was exceeded when upstream lake levels exceeded the normal RL158 level, rising as high as RL159.5 during major rainy periods." |  | Might suggest we look more closely at the relationship of rain storms to the metal sampling in 1999 when we saw the first spikes. Also there appear to be two high Ni spikes in Lois' 1999 data that doesn't match with data that Tony downloaded from the data base!
1999-12-01 | Flow-through 1km+ long; N8500-N9500 | 1999/bcdump_12_99 | Ore stockpile started on Cribhut level
BCD top elevation 220
mid 2000 | Mining in Centre Pit North | 2000/bcdump_06_00 | No dumping in BC. Ore Stockpiles developing on Cribhut level.
Ore Stockpiles developing on Cribhut level.
late 2000 | Extension 2 mining | 2000/bcdump_12_00 | Major ore stockpiles on Cribhut level
| Magnesite stockpile at Cribhut started |  | BCD top elevation 220
Ore stockpiles on Cribhut level
mid 2001 | Mining Ext 2 and dumping on top of flow-through | 2001/bcdump_06_01 | BCD top elevation 238
Ore stockpiles on Cribhut level
2001-08-01 | Magnesite stockpile at Cribhut pushed down into BC | 2001/bcdump_07_01
2001-12-01 | Ore stockpiles on Cribhut level | 2001/bcdump_12_01 | BCD top elevation 260
2002-06-01 | RL240 stockpile started and raised to RL250 | 2002/bcdump_06_02 | BCD top elevation 260
2002-12-01 | Most of RL240 stockpile removed | 2002/bcdump_12_02 | BCD top elevation 270 with clay stockpile above RL260
Cribhut stockpile removed and base resealed with clay
2003-12-01 | Large low grade stockpiles being built on RL260 level | 2003_dec_photo/dec03_all1.str
Extension of BCFT towards west (what became Waterfall Dump) and northwards started
2004 | Mining in Centre Pit | 2004/bcdump_06_04
2004-12-01 | CP stockpile placed behind South Lens crest commenced in July 04 | 2004/bcdump_12_04
2005-01-01 | Extension 135m northwards | 2005/bcdump0105bjh
2005-03-01 | "Skyway ramp" RL260-RL230 begun |  | Lois: This doesn't effect any environmental issue but I just wanted to include it in the history.
2005-04-01 | "skyway ramp" completed
2005-05-01 | Magnesite stockpile extended 15m in western corner.
2005-06-01 | Flow-through extension 100m northwards | 2005/bcdump0605
2005-07-01 | A-type armouring to northern and southern upper levels of BC dump
2005-10-01 | A-type extension arounf northern end of BC dump mentioned in End of Month report
2005-11-01 | Northern A-type extension experienced a failure thought to be due to placing A-type on top of a previous cly failure from the orignal dump.
2005-12-01 | Airphoto | 2005_dec_photo/dec05_all1
Jan-Mar06 | Extensions up Waterfall Creek | 2006/bcdump0306
2006-04-01 | Minor 40m northern extension to N100070. Minor westward advance in Waterfall Dump | 2006/upperbc0406 | 10070N
Tyre conduit placed in lower Broderick Creek
2006-05-01 | Jim's Dump started
2006-09-01 | Jims Dump completed to RL160 and south to N8240
2006-10-01 | Jim's Dump widened at N8240
Nov-Dec 06 | Jim's Dump extending westwards
Workshop fill begun
CP stockpile removed from behind South Lens crest
BC "lost" - note loss location is in same location as original creek bed
Workshop fill completed

## Lois' Graphs
These high concentration periods may correspond to the high upper "lake" levels above RL160 but we don't have a lot of data to compare.
Are these high Ni concentration correct. Out plot (see Metals) doesn't show these as being this high.
Are these cu levels of concern or is it only those past 2005?

## PreABM
Natural Surface
Pre ABM
Pre ABM with original creek
Pre ABM with original creek and 2003 PMI Diversion airphoto pick up
2003 PMI Diversion airphoto pick up
26m of fill
(also location of 2007 "lost" creek)
All of original Broderick Creek is buried under dumps
(500m gridlines)

## 1998
First extensions of BC dumps Jan-Jun 1998
Jun-Dec 1998

## 1999
BRODERICK CREEK FLOWTHROUGH 175 RL PLAN - June 1999
|  | 10250N |  |  |  | 10000N |  | 9750N |  |  | 9500N | 9250N |  |  | 9000N | 8750N |  | 8500N |  | 8250N |  | 8000N | 7750N
6750E
6500E
6250E
6000E
5750E
SCHEMATIC ONLY!
200
190
180
170
160
150
140
130
120
110
LONGITUDINAL SECTION
( SCALE ~1H:20V )
SCHEMATIC ONLY!
| 200 | [23 empty] | 200
| 190 | [23 empty] | 190
| 180 | [23 empty] | 180
| 170 | [23 empty] | 170
| 160 | [23 empty] | 160
| 150 | [23 empty] | 150
| 140 | [23 empty] | 140
| 130 | [23 empty] | 130
| 120 | [23 empty] | 120
| 110 | [23 empty] | 110
|  |  | E5900 | [5 empty] | E6000 |  |  |  |  | E6100 |  |  | E6200 |  |  |  | E6300 |  |  | E6400
SECTION N8750
SCHEMATIC ONLY!
| 230 | [17 empty] | L | [5 empty] | 230
| 220 | [23 empty] | 220
| 210 | [23 empty] | 210
| 200 | [23 empty] | 200
| 190 | [23 empty] | 190
| 180 | [23 empty] | 180
| 170 | [23 empty] | 170
| 160 | [23 empty] | 160
| 150 | [23 empty] | 150
| 140 | [23 empty] | 140
|  |  | E5900 | [5 empty] | E6000 |  |  |  |  | E6100 |  |  | E6200 |  |  |  | E6300 |  |  | E6400
SECTION N9300
INFLOW RL158-159,
DEPENDANT ON RAINFALL
175 contour
175 contour
South Lens
CLAY
A-TYPE
A/B TYPE
PRE-ABM FLOWTHROUGH DAM
D-TYPE
60% CLAY
& 40% D-TYPE
175 contour
PRE-ABM DIVERSION DAM
NOTES:
1. A-TYPE FLOWTHROUGH COMPLETED BETWEEN N8600 AND N9500 UP TO RL175.
2. SEVERAL CELLS OF D-TYPE ENCAPSULATED AND CAPPED BY CLAY. ONE SMALL AREA NEAR N9300 NOT BACKFILLED AT PRESENT.
3. CLAY CAPPING ON TOP OF RL175 85% COMPLETE. SHORT SECTION FROM N9150 TO N9300 STILL TO BE COMPLETED.
4.RL190 D-TYPE DUMP BEING CONSTRUCTED ON TOP OF FLOWTHROUGH FROM N8625 TO N900.
5. ASBESTOS DUMP ESTABLISHED N8900 E6150
RL'S 175-190
RL190 DUMP AND INTERIM ORE STOCKPILE BEING CONSTRUCTED
ASBESTOS DUMP, CLAY CAPPED, POLY LINED
D-TYPE
A-TYPE
PRE-ABM FLOWTHROUGH DAM
PRE-ABM DIVERSION DAM
CURRENT HYDRAULIC GRADIENT OF FLOW THROUGH:
(RL158.5-RL147) / 1000 = 0.0115
CLAY
CLAY OVERLAIN BY A-TYPE
OUTFLOW RL147
A-TYPE
CLAY
60% CLAY
& 40% D-TYPE
ORIGINAL GROUND WITH NATURAL CLAY NEAR SURFACE
D-TYPE
OLD PMI D-TYPE DUMPS WITH MINOR CLAY COVERINGS
MEGA RAMP
A/B TYPE
ORIGINAL GROUND WITH NATURAL CLAY NEAR SURFACE
A-TYPE
CLAY
ORIGINAL GROUND WITH NATURAL CLAY NEAR SURFACE
D-TYPE
OLD PMI D-TYPE DUMPS WITH MINOR CLAY COVERINGS
A/B TYPE
ORIGINAL GROUND WITH NATURAL CLAY NEAR SURFACE
Dec 1998
Jun 1999
Mar 1999
Dec 1999
Infilling creek
Infill of creek
complete
Flow-Through 1km+
in length
Ore stockpiles developing
RL173
Water Level RL147
RL200

## 2000
Jun 2000
Dec 1999
Ore stockpiles developing
Ore stockpiles well developed
Dec 2000
RL240
RL220
RL200

## 2001
Jun 2001
Dec 2000
Dec 2001
Magnesite stockpile development
Aug 2001
RL260
RL240
RL220
RL186
RL147

## 2002
Dec 2001
Jun 2002
Dec 2002
RL260
RL240 Ore stockpile developing
Cribhut ore stockpile empty; relined with clay

## 2003
Dec 2002
Jun 2003
Dec 2003
RL255 area being prepared for sealing and stockpile developemnt
RL240 stockpile cleared out
A-type armouring being placed over d/s clay lining
Westward extension of BCFT

## 2004
Dec 2003
Jun 2004
Dec 2004
Note: Mining in Centre Pit
Centre Pit Ore stockpile placed behind upper crest of South Lens
Dec 2003
July 2004

## 2005
Dec 2004
Dec 2005
Jan 2005
Northward extension of BCFT
Jun 2005
As shown below the magnesite stockpile was extended in the month of May 2005
Location of A-type failure on old clay slip

## 2006
Dec 2005
Mar06
Mar 2006
Dec 2006
Apr06
Sept06
Upper Broderick Creek
Lower Broderick Creek
May06
Sept06
Oct06
Nov06
Dec06

## Lake level data
Date | D/S Ch. | D/S Water Level | U/S Ch. | U/S Water Level | Flow-Through Length | Diff. In Water Level | Gradient | Comments
1998-09-11 |  | 148 |  | 152.4 | 330 | 4.4 | 0.013333 | <2mm of rain over previous two days
1998-09-23 |  | 148 |  | 156.7 | 330 | 8.7 | 0.026364 | day after 54mm of rain
1999-01-01 |  | 147.3 |  | 156.1 | 450 | 8.8 | 0.019556 | after 39mm of rain on 28/12/98
1999-01-18 |  | 147.5 |  | 151.9 | 500 | 4.4 | 0.0088 | after 2 weeks of little or no rain
1999-01-21 |  | 147.1 |  | 151.8 | 500 | 4.7 | 0.0094
1999-02-05 |  | 147.1 |  | 151
1999-03-12 |  | 147.1 |  | 151.6
1999-04-29 | 8550 | 147.1 | 9200 | 153.2 | 650 | 6.1 | 0.0093846
1999-05-11 | 8550 | 147.1 |  | 153
1999-05-17 | 8550 | 147.1 |  | 155.4
1999-05-18 | 8550 | 147.1 |  | 155.3
1999-05-20 | 8550 | 147.1 |  | 155.2 | 900 | 8.1 | 0.009 | A-type connected to northern end 22/5/99
1999-06-04 | 8550 | 147.12 | 9600 | 159 | 1050 | 11.88 | 0.011314
1999-06-05 12:00
1999-06-07 | 8550 | 147.1 | 9600 | 158.5 | 1050 | 11.4 | 0.010857
1999-06-08 | 8550 | 147.1 | 9600 | 158.5 | 1050 | 11.4 | 0.010857
1999-06-10 | 8550 | 145.8 | 9600 | 158 | 1050 | 12.2 | 0.011619
1999-07-06 | 8550 | 145.8 | 9600 | 158 | 1050 | 12.2 | 0.011619
1999-07-08 | 8550 | 145.8 | 9600 | 158.5 | 1050 | 12.7 | 0.012095
1999-07-16 | 8550 | 145.8 | 9600 | 157 | 1050 | 11.2 | 0.010667
1999-07-23 | 8550 | 145.8 | 9600 | 159 | 1050 | 13.2 | 0.012571
1999-07-26 | 8550 | 145.8 | 9600 | 159 | 1050 | 13.2 | 0.012571 | * minor overflow in Brett's Drain on 27/7/99
1999-07-29 | 8550 | 145.8 | 9600 | 158 | 1050 | 12.2 | 0.011619 | Brett's Drain overflow dry
1999-08-03 | 8550 | 145.8 | 9600 | 158.5 | 1050 | 12.7 | 0.012095 | * no overflow in Brett's Drain on 5/8/99
1999-08-10 | 8550 | 145.8 | 9600 | 158.5 | 1050 | 12.7 | 0.012095 | Brett's Drain overflow dry
1999-08-13 | 8550 | 145.8 | 9600 | 158.5 | 1050 | 12.7 | 0.012095 | Brett's Drain overflow dry
1999-08-16 | 8550 | 145.8 | 9600 | 158.5 | 1050 | 12.7 | 0.012095 | Brett's Drain overflow dry
1999-08-20 | 8550 | 145.8 | 9600 | 159.5 | 1050 | 13.7 | 0.013048 | minor overflow in Brett's Drain
1999-08-24 | 8550 | 145.8 | 9600 | 159 | 1050 | 13.2 | 0.012571
1999-08-31 | 8550 | 145.8 | 9600 | 158.5 | 1050 | 12.7 | 0.012095
1999-09-10 | 8550 | 145.8 | 9600 | 159 | 1050 | 13.2 | 0.012571 | Brett's Drain overflow dry
1999-09-17 | 8550 | 145.8 | 9600 | 158 | 1050 | 12.2 | 0.011619 | Drainage from old lg stockpile now in B's drain
1999-09-23 | 8550 | 145.8 | 9600 | 158.8 | 1050 | 13 | 0.012381
1999-10-04 | 8550 | 145.8 | 9600 | 157 | 1050 | 11.2 | 0.010667
1999-11-16 | 8550 | 145.8 | 9600 | 156 | 1050 | 10.2 | 0.0097143
1999-11-22 | 8550 | 145.8 | 9600 | 156 | 1050 | 10.2 | 0.0097143
1999-12-13 | 8550 | 145.8 | 9600 | 154 | 1050 | 8.2 | 0.0078095
1999-12-24 | 8550 | 145.8 | 9600 | 155 | 1050 | 9.2 | 0.0087619
2000-01-04 | 8550 | 145.8 | 9600 | 154 | 1050 | 8.2 | 0.0078095
2000-01-07 | 8550 | 145.8 | 9600 | 153.5 | 1050 | 7.7 | 0.0073333
2000-01-21 | 8550 | 145.8 | 9600 | 153.5 | 1050 | 7.7 | 0.0073333
2000-01-26 | 8550 | 145.8 | 9600 | 153.5 | 1050 | 7.7 | 0.0073333
2000-02-01 | 8550 | 145.8 | 9600 | 153.6 | 1050 | 7.8 | 0.0074286
2000-02-15 | 8550 | 145.8 | 9600 | 153.5 | 1050 | 7.7 | 0.0073333
2000-02-24 | 8550 | 145.8 | 9600 | 153.5 | 1050 | 7.7 | 0.0073333
2000-03-09 | 8550 | 145.8 | 9600 | 153.5 | 1050 | 7.7 | 0.0073333
2001-01-29 | 8550 | 145.8 | 9600 | 155 | 1050 | 9.2 | 0.0087619 | Reading prior to extending flow-through southwards
2001-06-30 | 8530 | 147.2 | 9600 |  | 1070
2001-07-30 | 8500 | 148.8 | 9600 |  | 1100
2003-12-30 | 8500 | 148.8 | 9740 | 159.65 | 1240 | 10.85 | 0.00875
2005-01-30 | 8500 | 148.8 | 9875 |  | 1375
2005-06-30 | 8500 | 148.8 | 9975 |  | 1475
2008-02-14 | 7700 | 100.9 | 10000 | 161.6 | 2300 | 60.7 | 0.026391
2008-03-13 | 7700 | 100.9 | 10000 | 159.8 | 2300 | 58.9 | 0.025609
2008-04-04 | 7700 | 100.9 | 10000 | 162.14 | 2300 | 61.24 | 0.026626
2008-05-19 | 7700 | 100.9 | 10000 | 163.59 | 2300 | 62.69 | 0.027257