## Financial Model
Razorback Mine Early Production Option - Preliminary Valuation (Pre-Scoping Study Level)
Year |  | Total | 1 | 2 | 3 | 4 | Razorback Base Case - Preliminary Valuation Summary
Ore production | :t | 200000 | 35000 | 70000 | 70000 | 25000 | LOM Ore(tonnes) | 200000 |  | 200000
Grade | :% | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | Peak Annual Production (t.p.a) | 70000 |  | 70000
ROM tin | :t | 1800 | 315 | 630 | 630 | 225 | Grade (%) | 0.9 |  | 0.9
Recovery | :% | 65 | 65 | 65 | 65 | 65 | Recovery (%) | 65 |  | 65
Tin produced | :t | 1170 | 204.75 | 409.5 | 409.5 | 146.25 | Capex (A$M) | 5.82 |  | 5.82
Conc grade | :% | 50 | 50 | 50 | 50 | 50 | Net Cash Flow (A$M) | 16.1282 |  | 16.1282
Conc produced | :t |  | 409.5 | 819 | 819 | 292.5 | NPV 10% pre-tax (A$M) | 12.195 |  | 12.195
[7 empty] | IRR | 388.6% |  | 388.6%
Tin price | :US$/t | 22500 | 22500 | 22500 | 22500 | 22500 | NPV/Capex | 2.0954 |  | 2.0954
Exhange rate | :US$/A$ | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | Payback Period (months) | 15
A$ tin price | :A$/t | 32142.8571 | 32142.8571 | 32142.8571 | 32142.8571 | 32142.8571
Gross revenue | :A$m | 37.6071 | 6.5813 | 13.1625 | 13.1625 | 4.7009 | Sensitivity Analysis - Tonnage and Grade (US$22,500 Tin Price, 65% Recovery)
| :A$/t ore | 188.0357 | 188.0357 | 188.0357 | 188.0357 | 188.0357 | NPV 10% Pre-Tax (A$M)
Transport cost | :A$m | 0.2925 | 0.051188 | 0.10238 | 0.10238 | 0.036563 | Tonnes | Tin Grade (%Sn)
Smelting | :A$m | 2.106 | 0.36855 | 0.7371 | 0.7371 | 0.26325 |  | 0.7 | 0.8 | 0.9 | 1 | 1.1
Royalty | :A$m | 1.7604 | 0.30808 | 0.61615 | 0.61615 | 0.22005 | 150000 | 3.6 | 5.9 | 8.2 | 10.5 | 12.8
Total realisation | :A$m | 4.1589 | 0.72781 | 1.4556 | 1.4556 | 0.51987 | 200000 | 6.3 | 9.2 | 12.2 | 15.2 | 18.1
| :A$/t ore | 20.7947 | 20.7947 | 20.7947 | 20.7947 | 20.7947 | 250000 | 8.9 | 12.5 | 16.2 | 19.8 | 23.4
| :A$/t tin | 3554.6429 | 3554.6429 | 3554.6429 | 3554.6429 | 3554.6429 | Undiscounted Net Cash Flow (A$M)
[7 empty] | Tonnes | Tin Grade (%Sn)
Net Revenue | :A$m | 33.4482 | 5.8534 | 11.7069 | 11.7069 | 4.181 |  | 0.7 | 0.8 | 0.9 | 1 | 1.1
Ore | :A$/t | 167.2411 | 167.2411 | 167.2411 | 167.2411 | 167.2411 | 150000 | 4.9 | 4.7 | 10.5 | 13.3 | 16.1
Tin | :A$/t | 28588.2143 | 28588.2143 | 28588.2143 | 28588.2143 | 32142.8571 | 200000 | 8.7 | 12.4 | 16.1 | 19.8 | 23.6
[7 empty] | 250000 | 12.4 | 17.1 | 21.7 | 26.4 | 31
Mining | :A$/t ore | 25 | 25 | 25 | 25 | 25
Transport | :A$/t ore | 0 | 0 | 0 | 0 | 0 | Sensitivity Analysis - Tin Price (Base Case)
Processing | :A$/t ore | 20 | 20 | 20 | 20 | 20 |  | Tin Price (US$/T)
Admin | :A$/t ore | 10 | 10 | 10 | 10 | 10 |  | 18500 | 20500 | 22500 | 24500 | 26500
Total cash cost | :A$/t ore | 55 | 55 | 55 | 55 | 55 | NPV 10% Pre-Tax (A$M) | 7.4 | 9.8 | 12.2 | 14.6 | 17
[7 empty] | Undiscounted Net Cashflow (A$M) | 10.1 | 13.1 | 16.1 | 19.1 | 22.1
Mining | :A$m | 5 | 0.875 | 1.75 | 1.75 | 0.625
Transport | :A$m | 0 | 0 | 0 | 0 | 0
Processing | :A$m | 4 | 0.7 | 1.4 | 1.4 | 0.5
Admin | :A$m | 2 | 0.35 | 0.7 | 0.7 | 0.25
Total cash cost | :A$m | 11 | 1.925 | 3.85 | 3.85 | 1.375
ore | :A$/t | 55 | 55 | 55 | 55 | 55
tin | :A$/t | 9401.7094 | 9401.7094 | 9401.7094 | 9401.7094 | 9401.7094
Cash profit | :A$m | 22.4482 | 3.9284 | 7.8569 | 7.8569 | 2.806
| :A$/t | 112.2411 | 112.2411 | 112.2411 | 112.2411 | 112.2411
Capex | :A$m | 6.32 | 5.82 | 0.3 | 0.2 | 0
Net Cash Flow |  | 16.1282 | -1.8916 | 7.5569 | 7.6569 | 2.806
NPV10% A$m |  | 12.195
IRR |  | 388.6%
Capex Summary
Mining | :A$m |  | 1.5
Processing | :A$m |  | 2.5
Tailings | :A$m |  | 0.7
Working Capital | :A$m |  | 0.5
Contingency | :A$m |  | 0.52
Maintenance | :A$m |  | 0.1 | 0.3 | 0.2
Total | :A$m |  | 5.82 | 0.3 | 0.2 | 0
Note on F5: Gary Fietz: Midpoint of Tim Callaghan 'resource' Estimate
Note on F7: Gary Fietz: Based on historic mining recovery based on best available information. Metallurgical testork TBC. Opportunity for improved recoveries with use of spirals and tables gravity plant.
Note on F12: Gary Fietz: Close to 2017-2019ytd average price
Note on F13: Gary Fietz: current Spot FX
Note on F18: Gary Fietz: As per Heemskirk SS/PFS Studies
Note on F19: Gary Fietz: As per Heemskirk SS/PFS Studies
Note on F20: Gary Fietz: As per Heemskirk SS/PFS Studies
Note on F29: Gary Fietz: Preliminary verbal estimate for simple underground mining 2 level operation with no backfill from Mining One (June 2019)
Note on F31: Gary Fietz: Based on benchmarks from other projects with simple gravity flowsheet (no tin floatation). Eg Redmoor
Note on F32: Gary Fietz: Internal Estimate
Note on H51: Gary Fietz: Tim Callaghan Estimate - assume will be same for accessing ~180mRL (100m below pit floor) with one sub level around 230mRL (ie 2* 50m levels)
Note on H52: Gary Fietz: Internal estimate based on a small (70Ktpa) simple gravity plant similar to that used previously at Razorback. Based on second hand crushers and ball mill and Chinese made screens, spirals and tables assembled in Tasmania on a skid mounted frame. As a comparative the Granville plant that AusTin is using could do 50ktpa and cost A$1-2m to build using scavenged equipment.
Note on H53: Gary Fietz: Internal Estimate based on re-use of existing tailings dams - new pipeline and building up wall heights
Note on H54: Gary Fietz: Internal Estimate
Note on H55: Gary Fietz: Internal Estimate
Note on H56: Gary Fietz: Internal Estimate

## Budget&Schedule
Razorback Early Production Project Pre-Construction Budget |  |  |  | Razorback Early Production Project Preliminary Schedule
| m drilled | days | AUD | Activity |  | Months from Completion of Funding
Probable Reserve Drilling (700m as per CP) | 700 | 35 | 175000 |  | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Resource Optimisation Drilling (N and FW Ext - 500m) | 500 | 25 | 125000 | Inferred Resource (July, already funded)
Inferred Resource Estimate (historic drilling) |  |  | 8400 | Razorback Inferred Resource Estimate | bar: -1
Total Razorback Probable Reserve and Optimisation Drilling | 1200 | 60 | 308400 | Razorback Inferred Resource Release | bar: -1
Geotech Testwork |  |  | 40000
Hydrogeology (1 Piezometer) |  |  | 30000 | Drilling and PFS
Metallurgical Testwork & Flowsheet design |  |  | 60000 | Razorback Drilling | bar: Months from Completion of Funding 2 to Months from Completion of Funding 3
Environmental Baseline suvey |  |  | 50000 | Analysis | bar: Months from Completion of Funding 4
Permitting |  |  | 42000 | Drilling Results Release - Batch 1 | bar: Months from Completion of Funding 3
Indicated Resource Estimate |  |  | 14400 | Drilling Results Release - Batch 2 | bar: Months from Completion of Funding 4
Mine Design, Capex and Opex |  |  | 50000 | Hydrogeological Testwork | bar: Months from Completion of Funding 3 to Months from Completion of Funding 5
Probable Reserve |  |  | 4800 | Geotech Testwork | bar: Months from Completion of Funding 3 to Months from Completion of Funding 4
Process Plant & Site Infrastructure Design Capex and Opex |  |  | 30000 | Metalurgical Testwork | bar: Months from Completion of Funding 4 to Months from Completion of Funding 5
PFS Report |  |  | 67500 | Metalurgical Testwork Results Release | bar: Months from Completion of Funding 6
Total Razorback PFS Costs |  |  | 388700 | Indicaded Resource Estimate | bar: Months from Completion of Funding 5
Pre-Construction Engineering, equipment sourcing |  |  | 50000 | Indicated Resource Estimate Release | bar: Months from Completion of Funding 6
Permitting |  |  | 42000 | Mining Study | bar: Months from Completion of Funding 5 to Months from Completion of Funding 6
BFS Report |  |  | 75000 | Processing Plant and Site Infrastructure Study | bar: Months from Completion of Funding 6 to Months from Completion of Funding 7
Total Razorback BFS Costs |  |  | 167000 | Environmental Baseline Studies | bar: Months from Completion of Funding 1 to Months from Completion of Funding 9
Core Shed/Office Rent |  |  | 14400 | Permiting* | bar: Months from Completion of Funding 1 to Months from Completion of Funding 12
Vehicle |  |  | 10000 | PFS Report | bar: Months from Completion of Funding 6 to Months from Completion of Funding 8
House Rent |  |  | 7200 | PFS Release | bar: Months from Completion of Funding 8
Geological Equipment |  |  | 15000
Senior Geologist (190 days) |  |  | 171000 | BFS
Field Assistant (9 months) |  |  | 37500 | Engineering and Equipment sourcing | bar: Months from Completion of Funding 9 to Months from Completion of Funding 10
Total Geology and Site Costs (12 months) |  |  | 255100 | BFS Report | bar: Months from Completion of Funding 11 to Months from Completion of Funding 12
BFS Release | bar: Months from Completion of Funding 12
Corporate Overhead (12 Months) |  |  | 600000
Construction Funding | bar: Months from Completion of Funding 11 to Months from Completion of Funding 13
Montana Flats Exploration (2 holes) |  |  | 180000 | Construction Funding Release | bar: Months from Completion of Funding 13
Grand Total |  |  | 1899200 | Construction
Mine Development | bar: Months from Completion of Funding 14 to Months from Completion of Funding 17
Process Plant | bar: Months from Completion of Funding 14 to Months from Completion of Funding 17
Production Commencement | bar: Months from Completion of Funding 18
Production Commencement | bar: Months from Completion of Funding 18
Montana Flats Exploration Drilling
Drilling (2 *600-700m holes) | bar: Months from Completion of Funding 4 to Months from Completion of Funding 5
Assays | bar: Months from Completion of Funding 6
Drilling Results Release | bar: Months from Completion of Funding 7
* Risk that Permittig time may be extended from 12 to 18m for processing and tailings storage at Razorback is required to be permited in addition to mine.